## Slide 1: TGF Salesforce AMS Weekly Report
April ‘23 2020

## Slide 2: Executive Summary
Project Phase - Transition Planning phase Project Start Date : 06th Apr ’20 | Week 3
Status | This Report | Previous Report | Trending
Overall Status |  |  | ↔
Scope |  |  | ↔
Budget |  |  | ↔
Resources |  |  | ↔
Timeline |  |  | ↔
Issues & Risks |  |  | ↔
Quality & Testing |  |  | ↔
Summary
Key Accomplishments this Week Internal KT Complete with Balaji’s team on Overall application overview & SNOW Other application overview – Sourcing and Procurement Change management, Support process Overview Studied documents for following modules: 1.GOS Overview 2.Master Data 3.Funding Request 4.PF & Budget Data Questionnaire prepared for modules 1. GOS Overview 2.Master Data Management 3.PF & Budget Data Key Accomplishments Planned for this Week Begin KT for High complex modules – GLCP - PF and budget data Funding Request [GLCP - IMM Fund Management]
Items for Attention | Status | Owner
Raise access needs for Cognizant team (SNOW, GOS, Sandboxes, TGF id User ID creation) and 1$ PO creation | InProgress | DC
Identify Stakeholders for KT and Block calendars | InProgress | DC/ Ganesh
Update Plan in Smartsheet | InProgress | DC/ Ganesh
Milestone Dates  KT Start Date : 24th April’20; KT End Date : 2nd June’20

## Slide 3: Executive Summary
Construct (Design/Build)
Plan & Discover
Validate
Deploy & Support
Project Phase - Sprint # 4 – OCV Mexico - Implementation & Migration Project Start Date : 06th Sept’19 | Weeks Completed : 24
Status | This Report | Previous Report | Trending
Overall Status |  |  | ↔
Scope |  |  | ↔
Budget |  |  | ↔
Resources |  |  | ↔
Timeline |  |  | ↔
Issues & Risks |  |  | ↔
Quality & Testing |  |  | ↔
Summary
Key Accomplishments Completed last Week Sprint- 1 PROD Deployment Completed Last 2 years LAN Regional org cases and Related Case duration records ,activities migrated to GME Production org. Key Accomplishments Planned, but not Completed Last Week Attachment Migration From LAN to GME Test – Waiting for LAN Regional org Deployment with GME Connected app setting Key Accomplishments Planned for this Week Attachment Migration from Regional LAN to GME Prod Last 2 year cases. LAN Regional org Email message migration to GME New Dashboards to measure KPI’s Live Agent for Mexico users Assignment rule change to route cases to Mexico Customer Interactions.
Items for Attention | Status | Owner
Phase -2 Sprint -1 moved to Production | Completed | Dev Team
Phase -2 Sprint -2 JIRA stories | InProgress | Dev Team
Attachment migration - Analysis and Design InProgress | InProgress | Dev Team
Current - Sprint 4
50%
Milestone Dates  Sprint 4 Start Date : 3nd June’19 ; Sprint 4 End Date : 1St Feb’20

## Slide 4
RAID Log Dashboard
 | OCV Mexico- RAID LOG DASHBOARD |  |  |  |  |  |  |  |  |  |  | 
 | Risk |  |  | Assumptions |  |  | Issues |  |  | Dependencies |  | 
 | 0 |  |  | 1 |  |  | 0 |  |  | 1 |  | 
 | LEVEL |  |  |  |  |  |  |  |  |  |  | 
 | 0 | HIGH |  | 0 | HiGH |  | 0 | HiGH |  | 0 | HiGH | 
 | 0 | MEDIUM |  |  |  |  |  |  |  |  |  | 
 | 0 | LOW |  | 1 | MEDIUM |  | 0 | MEDIUM |  | 1 | MEDIUM | 
 | TREND |  |  |  |  |  |  |  |  |  |  | 
 | 0 | DETERIORATING |  | 0 | LOW |  | 0 | LOW |  | 0 | LOW | 
 | 0 | NO CHANGE |  |  |  |  |  |  |  |  |  | 
 | 0 | IMPROVING |  |  |  |  |  |  |  |  |  | 
 | 0% | MITIGATED |  | 0% | UPHELD |  | 0% | CLOSED |  | 0% | COMMITTED | 

## Slide 5
Top 6 Risks/ Issues / Dependency – OCV Mexico
# | Category | Issue / Risk Description | Issue Resolution/Mitigation | Impact | Owner | Target Closure | Status
1 | Technical | Import Case related Attachments from LAN to GME | Integrating LAN and GME instance to bring the Case Attachment data | Timelines | Development Team | 3/21/2020 | In -Progress
2 | Dependency | Dependency on global transaction data - Credit Billing & Invoice | Dependency on Company 360 to provide API's for Credit Billing & Invoice. Only after the API's are received, we can take this up for the upcoming sprints. | Timelines | Company 360 team | 3/20/2020 | Pending
2

## Slide 6
Project Deliverables – OCV Mexico
Key Deliverables | Due Date | Status
LAN Regional org Case Migration to GME | 03/07/20 | Complete
Attachment Migration from LAN to GME | 03/21/20 | InProgress
Email Messages / Case related objects migration from LAN to GME | 03/21/20 | InProgress
Upcoming Offshore Holidays |  | 
Tamil New Year | April 14th | Tuesday