## Read me
Sl. No. | Key Considerations for the Transition Plan
1 | In view of the ongoing situation due to COVID-19 outbreak, certain activities in the "Knowledge Acquisition" phase such as Application Functional KT, Application Technical KT etc. which need involvement from TGF SME's will be organized using a combination of sessions with the India based team of the incumbent vendor and remote sessions arranged with relevant TGF stakeholders.
2 | We have identified an initial 2 week period - "Pre-Transition Preparation" during which we will identify resources needed for Transition, setup connectivity with TGF Salesforce environment from Offshore, Initiate and process access requests for the team and initiate travel logistics (e.g. VISA formalities) for associates who need to travel to Geneva during Secondary Support and Primary Support phases
3 | While our Proposal Response contained a 10 week Transition timeframe, we have taken a 2 week buffer as per the plan highlighted herein to factor for uncertainties due to the ongoing COVID-19 outbreak. -- An additional 2 weeks has been considered in the "Knowledge Acquisition" Phase (4 wks planned --> 6 wks as per current plan) Cognizant will re-assess Transition timelines during the initial Planning Phase and based on our assessment, we may revert to the 10 week timeframe as mentioned in our original response.
4 | Part of JT team is alread identified - 3 FTEs and remaining 3 for KT start is planed to be identified in next 3 weeks.

## Weekly Plan
Phases |  |  | Location | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14
| Owner | Status | time axis 2020-03-30 to 2020-07-03
Pre-Transition Preparation | bar: 2020-03-30 to 2020-04-10
Resource identification and finalization | Velu |  | India | bar: 2020-03-30 to 2020-04-10
Finalize the access needs for Cognizant team (SNOW, GOS, Sandboxes, TGF id) | Irina |  | India | bar: 2020-04-02 to 2020-04-08
Raise requests for access & Track the status of Access requests | Velu |  | India | bar: 2020-04-03 to 2020-04-08
Setup Connectivity to environment (existing Salesforce Applications and tool access) |  |  | India | bar: 2020-03-30 to 2020-04-08
Walkthough of existing Application landscape, Current Incident Mgmt. & Change Mgmt. processes and Communication templates being followed with current AMS Team | Velu |  | India | bar: 2020-04-01 to 2020-04-10
Arrange travel logistics and finalize travel plans |  |  | India | bar: 2020-03-30 to 2020-04-10
Transition Planning Phase | bar: 2020-04-13 to 2020-04-24
Collect existing documents (Application Design docs, Process Maps, Support Process documents etc.) | DC | Week of 13th | India/Remote | bar: 2020-04-13 to 2020-04-17
Study existing documents and identify gaps and build Questionnaire | Velu |  | India/Remote | bar: 2020-04-13 to 2020-04-21
Identify stakeholders for KT sessions | DC | Week of 13th | India/Remote | bar: 2020-04-13 to 2020-04-14
Block calendars | DC |  | India/Remote | bar: 2020-04-14 to 2020-04-15
Finalize KT templates and Identify entry/exit criteria for all the phases | Velu / DC |  | India/Remote | bar: 2020-04-16 to 2020-04-24
Finalize Transition Timelines |  | Week of 13th | India/Remote | bar: 2020-04-16 to 2020-04-24
Milestone : KT Plan Sign-off |  |  | -
Knowledge Acquisition Phase | bar: 2020-04-27 to 2020-06-05
Application Functional KT | bar: 2020-04-27 to 2020-05-20
Overall Application Landscape |  |  | India/Remote | bar: 2020-04-27 to 2020-04-28
Grant Operating System (GOS) |  |  | India/Remote | bar: 2020-04-29 to 2020-05-06
Strategy Implementation Plan Tracker (SIP Tool) |  |  | India/Remote | bar: 2020-05-07 to 2020-05-08
Procurement KPI Reporting (Sourcing Portal) |  |  | India/Remote | bar: 2020-05-11 to 2020-05-12
Distribution List Management & External User Provisioning |  |  | India/Remote | bar: 2020-05-13
Reverse KT sessions with Incumbent team |  |  | India | bar: 2020-05-07 to 2020-05-14
Assessment and Review with TGF |  |  | India/Remote | bar: 2020-05-15 to 2020-05-20
Application Technical KT | bar: 2020-05-04 to 2020-06-03
Force.com |  |  | India/Remote | bar: 2020-05-04 to 2020-05-18
Community Portal |  |  | India/Remote | bar: 2020-05-19 to 2020-05-20
Wave Analytics |  |  | India/Remote | bar: 2020-05-21 to 2020-05-22
Ancillary tools |  |  | India/Remote | bar: 2020-05-25 to 2020-05-28
Integration |  |  | India/Remote | bar: 2020-05-21 to 2020-05-26
Reverse KT sessions with Incumbent team |  |  | India | bar: 2020-05-21 to 2020-05-28
Assessment and Review with TGF |  |  | India/Remote | bar: 2020-05-29 to 2020-06-03
Support and Enhancement Operations KT | bar: 2020-05-04 to 2020-05-29
Current ITIL Processes, Overview of Incident Management, Overview of Service Request |  |  | India | bar: 2020-05-04 to 2020-05-15
Lifecycle of Incident at TGF (Opening, review, workflow, processes, approvals, closing), Incident Reporting, Setting Priority to incidents, Ageing in Incidents, SLAs |  |  | India | bar: 2020-05-18 to 2020-05-29
QA KT | bar: 2020-05-11 to 2020-06-03
Automation Testing Overview and Test Scripts |  |  | India | bar: 2020-05-11 to 2020-05-14
Regression Testing Suite overview |  |  | India | bar: 2020-05-15 to 2020-05-20
PROVAR and Selenum Tool Understanding |  |  | India | bar: 2020-05-20 to 2020-05-25
PMO Toolkit review |  |  | India | bar: 2020-05-26
Reverse KT sessions with Incumbent team |  |  | India | bar: 2020-05-21 to 2020-05-28
Assessment and Review with TGF |  |  | India/Remote | bar: 2020-05-29 to 2020-06-03
Environment Management KT
Configuration Management Process Understanding |  |  | India/Remote | bar: 2020-05-18 to 2020-05-20
Understanding of Release Management |  |  | India/Remote | bar: 2020-05-21 to 2020-05-25
Tool Overview : SonarQube, GitHub, Jenkins etc. |  |  | India/Remote | bar: 2020-05-26 to 2020-05-29
Reverse KT sessions with Incumbent team |  |  | India | bar: 2020-05-25 to 2020-06-01
Assessment and Review with TGF |  |  | India/Remote | bar: 2020-06-02 to 2020-06-05
Secondary Support (Shadow) Phase | bar: 2020-06-08 to 2020-06-19
Observe & monitor incumbent support team |  |  | India + Geneva | bar: 2020-06-08 to 2020-06-19
Resolve Incidents and SR's under watch of existing support team |  |  | India + Geneva | bar: 2020-06-08 to 2020-06-19
Ticket Baselining and addressing Open Backlogs |  |  | India + Geneva | bar: 2020-06-08 to 2020-06-19
Formalize the communication approach/medium |  |  | India + Geneva | bar: 2020-06-08 to 2020-06-19
Primary Support (Lead) Phase | bar: 2020-06-22 to 2020-07-03
Assume primary support for Incidents and SR's |  |  | India + Geneva | bar: 2020-06-22 to 2020-07-03
SOP creation and update |  |  | India + Geneva | bar: 2020-06-22 to 2020-07-03
Finalize KPI's and Metrics |  |  | India + Geneva | bar: 2020-06-22 to 2020-07-03
Transition exit sign-off |  |  | Geneva
KT Progress Tracking and Status Reporting |  |  | -

## Knowledge Acquisition Details
Knowledge Acquisition Pillars | Incumbent Vendor PoC | Cognizant PoC | TGF PoC | No. of Days | Planned Hours/day | Total Hrs. Planned | To be filled after the KT session
[7 empty] | Session Completed Date | Session Completed Time (CET) | Attendees TGF | Attendees IBM | Attendees Cognizant | % complete | RAG | Issues/ Risks | Recording Uploaded (Y/N) | Follow up Needed (Y/N) | Remarks | Planned No of Hours | Completed No of Hours | Remarks TGF
Application Functional KT
Overall Application Landscape
Overview of Application landscape including Salesforce ecosystem and Integration with GFS, SharePoint, WorkDay, BI and other systems via DataHub | TBD | TBD | TBD | 2 | 4 | 8
Grant Operating System (GOS) |  |  |  | 6 | 4 | 24
Grant Allocation Management | TBD | TBD | TBD | 1 | 4 | 4
Grant Making and Revision | TBD | TBD | TBD | 1 | 4 | 4
Funding Request Management | TBD | TBD | TBD | 1 | 3 | 3
Investment Management | TBD | TBD | TBD | 1 | 2 | 2
Portfolio Management | TBD | TBD | TBD | 1 | 2 | 2
LFA Management | TBD | TBD | TBD | 1 | 1 | 1
Grant Disbursement & Closure | TBD | TBD | TBD | 1 | 2 | 2
Financial Risk & Assurance | TBD | TBD | TBD | 1 | 2 | 2
Master Data Management | TBD | TBD | TBD | 1 | 2 | 2
Recoveries, UQD/PAAR and Differentiation | TBD | TBD | TBD | 1 | 2 | 2
Strategy Implementation Plan Tracker (SIP Tool)
Strategy Implementation Plan, Project Management and Risk Assessment | TBD | TBD | TBD | 2 | 4 | 8
Procurement KPI Reporting (Sourcing Portal)
Supplier Management and Reporting | TBD | TBD | TBD | 2 | 4 | 8
Distribution List Management & External User Provisioning
Partner Access Management | TBD | TBD | TBD | 1 | 2 | 2
Application Technical KT
Force.com
Understanding Data Model of the 4 applications - GOS, SIP, Sourcing Portal and Distribution List Management applications | TBD | TBD | TBD | 2 | 4 | 8
Salesforce Configuration - Analysis (Profile, Custom Objects, Permission Sets etc.) | TBD | TBD | TBD | 3 | 4 | 12
Salesforce Customization - Analysis (Apex, VF Pages, Lightning Components) | TBD | TBD | TBD | 6 | 4 | 24
Community Portal |  |  |  | 2 | 4 | 8
Community Portal Components | TBD | TBD | TBD | 1 | 4 | 4
Portal Configuration | TBD | TBD | TBD | 1 | 4 | 4
Wave Analytics |  |  |  | 2 | 4 | 8
Data model | TBD | TBD | TBD | 1 | 4 | 4
Data flow between Analytics and force.com applications | TBD | TBD | TBD | 1 | 4 | 4
Ancillary tools |  |  |  | 4 | 4 | 16
X-Author | TBD | TBD | TBD | 1 | 6 | 6
Conga | TBD | TBD | TBD | 1 | 1 | 1
Adobe e-Sign | TBD | TBD | TBD | 1 | 2 | 2
GridBuddy | TBD | TBD | TBD | 1 | 3 | 3
Odaseva Backup solution | TBD | TBD | TBD | 1 | 4 | 4
Integration |  |  |  | 4 | 3 | 12
Interface Overview | TBD | TBD | TBD | 2 | 3 | 6
Integration routines | TBD | TBD | TBD | 2 | 3 | 6
Support and Enhancement Operations KT
Current ITIL Processes, Overview of Incident Mgmt. and Service Request | TBD | TBD | TBD | 10 | 1 | 10
Lifecycle of Incident at TGF (Opening, review, workflow, processes, approvals, closing), Incident Reporting, Setting Priority to incidents, Ageing in Incidents, SLAs | TBD | TBD | TBD | 10 | 1 | 10
QA KT
Automation Testing Overview and Test Scripts | TBD | TBD | TBD | 4 | 4 | 16
Regression Testing Suite overview | TBD | TBD | TBD | 4 | 4 | 16
PROVAR and Selenum Tool Understanding | TBD | TBD | TBD | 4 | 4 | 16
PMO Toolkit review | TBD | TBD | TBD | 1 | 2 | 2
Environment Management KT
Configuration Management Process Understanding | TBD | TBD | TBD | 3 | 4 | 12
Understanding of Release Management | TBD | TBD | TBD | 3 | 4 | 12
Tool Overview : SonarQube, GitHub, Jenkins etc. | TBD | TBD | TBD | 4 | 4 | 16