## KT Calender Overview
| Sunday | Monday | Tuesday | Wednesday | Thusday | Friday | Saturday
Mar-2020 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-01-20
KT-Salesforce Org Readiness & Landscape
Webex
| 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27
|  | KT-Application Business Overview | KT-Application Business Overview | KT-Application Business Overview | KT-Application Functional Overview | KT-Application Functional Overview
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
|  | KT- Application Security Management | KT - Application Technical Overview | KT - Application Technical Overview | KT-Existing Application Modules | KT-Existing Application Modules
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
|  | KT-Existing Application Modules | KT-Application Modules Technical Specifications | KT-Application Modules Technical Specifications | KT-Application Modules Technical Specifications | KT-Support Tasks & Processes.
|  | Webex | Webex | Webex | Webex | Webex
Apr-2020 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17
|  | KT-Support Tasks & Processes. | KT-Play Back Session | KT-Play Back Session | KT-Shadow | KT-Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24
|  | KT-Shadow | KT-Shadow | KT-Shadow | KT-Shadow | KT-Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01
|  | KT-Shadow | KT-Shadow | KT-Shadow | KT-Shadow | KT-Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-02 | 1900-01-03 | 2020-04-05 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08
|  | KT-Shadow | KT-Shadow | KT-Shadow | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex | In Person | In Person
May-2020 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15
|  | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow
|  | Webex | In Person | In Person | In Person | In Person
| 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22
|  | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24
|  | Rev Shadow | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex
| 2016-12-25 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2020-05-01

## KT Calender Detail
Application Name |  | Bayer ServiceMax |  | Backed By Bayer |  | KA Start Date | 2020-03-20
Bayer SME | [5 empty] | KA End Date | 2020-04-15
Cognizant SME / Lead | [8 empty] | * Approximate KT start date provided. Upon further confirmation date will be finalized.
Session # | Application / Module / Component | KT Area | Bayer SME | Cognizant SME & Team | Planned Session Date | Planned Session start Time | Planned Session End Time | Calendar Invite Send? | Session Completed? | Comments
1 | Salesforce Org Readiness | Request Access for Cognizant Salesforce Associates |  |  | 2020-03-20 |  | 2020-03-20 | No | No
2 |  | Remedy Access and App ExcangeProducts, Required Integration System access. | [5 empty] | No | No
3 | Application Business & Functional Overview and Security Management. | Business Overview, Process Flow, Functional Overview and Integration Touchpoints. |  |  | 2020-03-23 |  | 2020-03-27 | No | No
4 |  | Security Settings, Profile and Permission Setup for ServiceMax Application | [5 empty] | No | No
5 | Salesforce Org Landscape & Existing Documnetations | Understanding of Salesforce Org & Release Management Strategy |  |  | 2020-03-30 |  | 2020-03-30 | No | No
6 |  | Standard Operation Procedures, RCA's, Best practice and Standards | [5 empty] | No | No
7 |  | SME details for the application and Document Folders (SharePoint and other repository)
8 | Application Technical Overview | ServiceMax Application data model walkthrough (Standard & Custom Objects) |  |  | 2020-03-31 |  | 2020-04-01 | No | No
9 |  | ServiceMax Application Setup & Configurations Overview, and specific ServiceMax Settings Overview | [5 empty] | No | No
10 | Application Exisiting Moducles and Technical Specifications | Customer Engagement Management |  |  | 2020-04-02 |  | 2020-04-09 | No | No
11 |  | Contract and Warranty Management | [5 empty] | No | No
12 |  | Work Order Management | [5 empty] | No | No
13 |  | Inventory, Logistics, and Parts Planning | [5 empty] | No | No
14 |  | Workforce Forecasting and Planning (Supply and Demand) | [5 empty] | No | No
15 |  | Scheduling and Routing | [5 empty] | No | No
16 |  | Console Configurations | [5 empty] | No | No
17 |  | Mobile App Configurations & Customizations | [5 empty] | No | No
18 |  | Integration, Analytics and Reporting | [5 empty] | No | No
19 | Support Tasks & Processes | Understanding of Configuration Management |  |  | 2020-04-10 |  | 2020-04-13 | No | No
20 |  | Understanding of Change Management / Break Fix | [5 empty] | No | No
21 |  | Understanding Monthly and Yearly Salesforce Business process ( If any) | [5 empty] | No | No
22 |  | Understanding Regulatory compliance Specific Process ( e.g. SOX Process) | [5 empty] | No | No
23 | Play Back Session | Playback Session covering Interface Overview / Support Tasks / Service Details/ IT Strategic Plan |  |  | 2020-04-14 |  | 2020-04-15 | No | No

## Sessions Plan
[7 empty] | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13
# | Task Name | Start Date | End Date | Session Status
|  |  |  | Planned | Actual | Completion % | W1 | W2 | W3 | W4 | W4
Bayer ServiceMax Transition Plan |  | 2020-03-20 | 2020-04-15 | 19 | 0 | 0%
1 | Salesforce Org Readiness | 2020-03-20 | 2020-03-20 | 1 | 0 | 0%
2 | Application Business & Functional Overview and Security Management. | 2020-03-23 | 2020-03-27 | 5 | 0 | 0%
3 | Salesforce Org Landscape, Release Management Strategy & Existing Documnetations | 2020-03-30 | 2020-03-30 | 1 | 0 | 0%
4 | Application Technical Overview | 2020-03-31 | 2020-04-01 | 2 | 0 | 0%
5 | Application Exisiting Moducles and Technical Specifications | 2020-04-02 | 2020-04-09 | 6 | 0 | 0%
6 | Application Support Schedule & Communication Plan | 2020-04-10 | 2020-04-10 | 1 | 0 | 0%
7 | Support Tasks & Processes | 2020-04-13 | 2020-04-13 | 1 | 0 | 0%
8 | Play Back Sessions | 2020-04-14 | 2020-04-15 | 2 | 0 | 0%

## Transaction Plan - ServiceMax
Bayer Salesforce ServiceMax Support Transition Plan
Sender | Bayer ServiceMax
Receiver | Cognizant Team
ID | Topic / Task Name | Duration | Start | Finish | Bayer SME Details - Application | Bayer POC | Location (Onsite / Offshore)
Salesforce Bayer ServiceMax Transition Plan
1 | Salesforce Org Readiness | 1 hr
1.1 | Request Access for Cognizant Salesforce Associates
1.2 | Bayer Email / Local Network / Remedy or Required Ticketing System access
1.3 | Salesforce Org Access
1.4 | Any Other Access required for Support - App Exchange Productions & Integration System
2 | Documentation and configuration | 1.5 hr
2.1 | Identification and collation of existing Salesforce application documentation
2.2 | Inventory of Application and Support Documents (Functional, Technical documents, etc.)
2.3 | Standard Operation Procedures, RCA's, Best practice and Standards
2.4 | Document Folders (SharePoint and other repository)
2.5 | SME details for the applications
3 | Salesforce Org Landscape | 1.5 hr
3.1 | Understanding of Salesforce Org Strategy
3.2 | Sandbox Refresh Strategy
3.3 | Release Management Strategy
4 | Salesforce Org - ServiceMax Security Configuration & Management | 1 day
4.1 | Security Controls | 1.5 hr
4.2 | Access restriction - IP Level
4.3 | Profile and Permission Set for Org and ServiceMax Application Level
4.4 | OWD- High level for Org and ServiceMax Application Level
4.5 | Salesforce Org Hierarchy
4.6 | SSO Setup Detail Walkthrough, if any
5 | ServiceMax Application - Business & Functional Overview | 4 days
5.1 | Business Overview | 1.5 hr
5.2 | Business function of application
5.3 | Business process Flow | 1.5 hr
5.4 | Overview of Application End to End architecture
5.5 | Authentication, Security and Identity in Mobile apps | 1.5 hr
5.6 | Known Errors and Issues
5.7 | Integration touchpoints - Functional Overview (Others) | 1.5 hr
5.8 | Others
6 | ServiceMax Application - Technical Specifications Overview | 2 days
6.1 | ServiceMax Application data model walkthrough (Standard & Custom Objects) | 1.5 hr
6.1 | ServiceMax Application Setup & Configurations Overview
| ServiceMax Application Customization Overview | 1.5 hr
ServiceMax Settings Overview
7 | ServiceMax Application Modules Functional & Technical Overview | 6 days
7.1 | Customer Engagement Management | 1.5 hr
7.2 | Contract and Warranty Management
7.3 | Work Order Management | 1.5 hr
7.4 | Inventory, Logistics, and Parts Planning | 1.5 hr
7.5 | Workforce Forecasting and Planning (Supply and Demand) | 1.5 hr
7.6 | Scheduling and Routing
7.7 | Console Configurations | 1.5 hr
7.8 | Mobile App Configurations & Customizations
7.9 | Integration | 1.5 hr
8 | Analytics and Reporting
8 | Application Open Issues & Known Error Overview | 1 days
8.1 | Current Challenges/Pain areas/ Areas of improvement in the project | 2 hr
8.2 | Recently raised Defect/Incident walkthrough along with resolutions
8.3 | Frequently Occurring Issues& Remedies
8.4 | Walk through of the recent changes that has been implemented
9 | Application Support Schedule & Communication Plan | 1 day
9.1 | Collation of stake holder information and Communication Process with Various Stakeholders | 2 hr
9.2 | Support Schedule
9.3 | Routine maintenance activities involved
10 | Ticketing Process & Details
10.1 | Understanding of Incident Management
10.2 | Understanding of Problem Management
10.3 | Understanding of Change Management / Break Fix
10.4 | Understanding of Configuration Management
10.5 | Understanding of Release& Deployment Management ( Application & Salesforce Feature Release )
10.6 | Understanding of Outage Planning / Business Continuity plan / Salesforce Backup Strategy /Disaster Recovery Plan
10.7 | Understanding of Salesforce Test Management Process.
10.8 | Understanding Monthly and Yearly Salesforce Business process ( If any)
10.9 | Understanding Regulatory compliance Specific Process ( e.g. SOX Process)
11 | Miscellaneous Details
11.1 | On going enhancements/development
11.2 | Vendor Support Agreements
11.3 | Existing documentation quality.
11.4 | Key Contact for different dependent application/platform.
11.5 | Any code Access restriction for offshore for any cots products and workarounds.
11.6 | Future Roadmap of the Application.
11.7 | Assumptions, Dependencies and Risks
11.8 | Non Functional Requirements
11.9 | Governance - Technical, Functional.
12 | Shadow | 15 Days
12.1 | Reverse KT Presentation and Q& A session with the SME's.
12.2 | Operational Readiness Check | 15 Days
13 | Reverse Shadow
14 | Sign Off