## Read me
Sl. No. | Key Considerations for the Transition Plan
1 | In view of the ongoing situation due to COVID-19 outbreak, certain activities in the "Knowledge Acquisition" phase such as Application Functional KT, Application Technical KT etc. which need involvement from TGF SME's will be organized using a combination of sessions with the India based team of the incumbent vendor and remote sessions arranged with relevant TGF stakeholders.
2 | We have identified an initial 2 week period - "Pre-Transition Preparation" during which we will identify resources needed for Transition, setup connectivity with TGF Salesforce environment from Offshore, Initiate and process access requests for the team and initiate travel logistics (e.g. VISA formalities) for associates who need to travel to Geneva during Secondary Support and Primary Support phases
3 | While our Proposal Response contained a 10 week Transition timeframe, we have taken a 2 week buffer as per the plan highlighted herein to factor for uncertainties due to the ongoing COVID-19 outbreak. -- An additional 2 weeks has been considered in the "Knowledge Acquisition" Phase (4 wks planned --> 6 wks as per current plan) Cognizant will re-assess Transition timelines during the initial Planning Phase and based on our assessment, we may revert to the 10 week timeframe as mentioned in our original response.
4 | Part of JT team is alread identified - 3 FTEs and remaining 3 for KT start is planed to be identified in next 3 weeks.

## KT Calender Overview
| Sunday | Monday | Tuesday | Wednesday | Thusday | Friday | Saturday
Apr-2020 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
|  | Pre transition phase | Pre transition phase | Pre transition phase | Pre transition phase | HOLIDAY
|  | Webex | Webex | Webex | Webex
| 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17
|  | Pre transition phase | HOLIDAY | Pre transition phase | Transition Planning | Transition Planning
|  | Webex |  | Webex | Webex | Webex
| 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24
|  | Transition Planning | Transition Planning | Transition Planning | Transition Planning | TGF Overview KT
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01
|  | High Complx Module KT | High Complx Module KT | High Complx Module KT | High Complx Module KT | High Complx Module KT
|  | Webex | Webex | Webex | Webex | Webex
May-2020 | 1900-01-02 | 1900-01-03 | 2020-04-05 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08
|  | High Complx Module KT | High Complx Module KT | High Complx Module KT | High Complx Module KT | High Complx Module KT
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15
|  | High Complx Module KT | High Complx Module KT | Med Complex Mod KT | Med Complex Mod KT | Med Complex Mod KT
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22
|  | Med Complex Mod KT | Med Complex Mod KT | Med Complex Mod KT | Med Complex Mod KT | Med Complex Mod KT
|  | QA Process & KT | QA Process & KT | QA Process & KT | QA Process & KT | QA Process & KT
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29
|  | Low Complex Mod KT | Low Complex Mod KT | Low Complex Mod KT | Low Complex Mod KT | Low Complex Mod KT
|  | QA Process & KT | QA Process & KT | QA Process & KT | QA Process & KT | QA Process & KT
|  | Webex | Webex | Webex | Webex | Webex
Jun-2020 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
|  | Support Process KT | Support Process KT | Support Process KT | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19
|  | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow | Rev Shadow
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26
|  | Rev Shadow | Rev Shadow | Rev Shadow | Primary Support | Primary Support
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
|  | Primary Support | Primary Support | Primary Support | Primary Support | Primary Support
|  | Webex | Webex | Webex | Webex | Webex
Jul-2020 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
|  | Primary Support | Primary Support | Primary Support | Primary Support | Primary Support
|  | Webex | Webex | Webex | Webex | Webex
| 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17
|  | Primary Support | Primary Support | Primary Support
|  | Webex | Webex | Webex
| 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24
| 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01

## KT Calender Detail
Application Name |  | Grant Management |  | Backed By TGF |  | KA Start Date | 2020-04-06
TGF SME | [5 empty] | KA End Date | 2020-06-15
Cognizant SME / Lead
Session # | Application / Module / Component | KT Area | TGF SME | Cognizant SME & Team | Planned Session Date | Planned Session End Time | Calendar Days | Calendar Invite Send? | Session Completed? | Comments
1 | Pre transition Preparation | Resource identification and finalization |  |  | 2020-04-06 | 2020-04-15 | 6 | No | No
2 |  | High level plan preparation for the KT phase | [5 empty] | No | No
3 | Transition Planning Phase | Study existing documents and identify gaps and build Questionnaire |  |  | 2020-04-16 | 2020-04-23 | 6 | No | No
4 |  | Identify stakeholders for KT sessions and finalize transition timelines | [5 empty] | No | No
5 | High Complex modules KT Sessions | Functional overview of high complex modules |  |  | 2020-04-24 | 2020-05-12 | 13 | No | No
6 |  | Detailed technical walkthrough of high complex modules | [5 empty] | No | No
7 |  | Discuss on known issues in the high complex modules
8 | Medium Complex modules KT Sessions | Functional overview of medium complex modules |  |  | 2020-05-13 | 2020-05-22 | 8 | No | No
Detailed technical walkthrough of medium complex modules
9 |  | Discuss on known issues in the medium complex modules | [5 empty] | No | No
10 | Low Complex modules KT Sessions | Functional overview of low complex modules |  |  | 2020-05-25 | 2020-05-29 | 5 | No | No
Detailed technical walkthrough of low complex modules
17 |  | Discuss on known issues in the low complex modules | [5 empty] | No | No
23 | QA Process & Tool KT | Automation Testing Overview and Test Scripts |  |  | 2020-05-18 | 2020-05-29 | 10 | No | No
19 |  | PROVAR and Selenum Tool Understanding | [5 empty] | No | No
23 | DevOps KT | Understanding of Release & Deployment Management ( Application & Salesforce Feature Release ) |  |  | 2020-05-18 | 2020-05-29 | 10 | No | No
19 |  | Understanding of DevOps process and usage of TGF SonarQube , GitHub , Jenkins | [5 empty] | No | No
19 | Support Tasks & Processes | Environment, Release & Change Management KT |  |  | 2020-06-01 | 2020-06-03 | 3 | No | No
21 |  | Understanding Regulatory compliance Specific Process ( e.g. SOX Process) Tool Overview : SonarQube, GitHub, Jenkins etc. | [5 empty] | No | No
19 | Secondary Support - Shadow phase | Resolve Incidents and SR's under watch of existing support team |  |  | 2020-06-04 | 2020-06-24 | 15 | No | No
20 |  | Observe & monitor incumbent support team | [5 empty] | No | No
19 | Primary Support - Lead Phase | Assume primary support for Incidents and SR's |  |  | 2020-06-25 | 2020-07-15 | 15 | No | No
20 |  | SOP creation and update | [5 empty] | No | No
| High Complex modules |  | KT Duration in days | Session Count / Module
Parallel Sessions | GLCP - PF and budget data | Funding Request | 4 | 7
| Grant Making (Lightning) | Grant Revisions | 4
| Annual Funding Decisions and Disbursements | Progress reports | 4
|  | Total days for High Complex Module | 12
| Medium Complex modules |  | KT Duration in days | Session Count / Module
Parallel Sessions | GLCP - Integration | Integrated Risk Management (IRM) | 2 | 4
| GLCP - IMM Grant Signing Calculator | Grant Closure | 2
| Local Fund Agent management | SIP & Sourcing Tool | 2
| Master Data management | Distributor List Mgmt & External Provisioning | 2
|  | Total days for Medium Complex Module | 8
| Low Complex modules |  | KT Duration in days | Session Count
Parallel Sessions | Grant Implementation | Investment Management (Lightning) | 2 | 3
| Financial Management Impact Review (Lightning) | Recoveries Management | 2
| External Audit Tracking (Lightning) | - | 1
|  | Total days for Low Complex Module | 5
Note on I7: Holidays excluded
Note on I11: 1 Day General Overview + 12 Days for High Complex modules

## Meeting Schedule
Knowledge Acquisition Phase ( KA ) - Week 1
Date | 2020-04-27 |  | 2020-04-28 |  | 2020-04-29 |  | 2020-04-30 |  | 2020-05-01
DAY | 2 |  | 3 |  | 4 |  | 5 |  | 6
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Topic 1 | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | GLCP - PF and budget data | Grant Making (Lightning) | Grant Making (Lightning)
Time
Module Complexity | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH
IBM POC
TGF POC
Cog POC | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A
Topic 2 | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Funding Request [GLCP - IMM Fund Management] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader]
IBM POC
TGF POC
Cog POC | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B
Knowledge Acquisition Phase ( KA ) - Week 2
Date | 2020-05-04 |  | 2020-05-05 |  | 2020-05-06 |  | 2020-05-07 |  | 2020-05-08
DAY | 7 |  | 8 |  | 9 |  | 10 |  | 11
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Time
Topic 1 | Grant Making (Lightning) | Grant Making (Lightning) | Grant Making (Lightning) | Grant Making (Lightning) | Grant Making (Lightning) | Grant Making (Lightning) | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements
Module Complexity | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH | HIGH
IBM POC
TGF POC
Cog POC | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A
Topic 2 | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Progress reports | Progress reports | Progress reports | Progress reports
IBM POC
TGF POC
Cog POC | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B
Knowledge Acquisition Phase ( KA ) - Week 3
Date | 2020-05-11 |  | 2020-05-12 |  | 2020-05-13 |  | 2020-05-14 |  | 2020-05-15
DAY | 12 |  | 13 |  | 14 |  | 15 |  | 16
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Time
Topic 1 | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements | Annual Funding Decisions and Disbursements | GLCP - Integration | GLCP - Integration | GLCP - Integration | GLCP - Integration | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report]
Module Complexity | HIGH | HIGH | HIGH | HIGH | MED | MED | MED | MED | MED | MED
IBM POC
TGF POC
Cog POC | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A
Topic 2 | Progress reports | Progress reports | Progress reports | Progress reports | Integrated Risk Management (IRM) [GLCP – Risk] | Integrated Risk Management (IRM) [GLCP – Risk] | Integrated Risk Management (IRM) [GLCP – Risk] | Integrated Risk Management (IRM) [GLCP – Risk] | Investment Management (Lightning) | Investment Management (Lightning)
IBM POC
TGF POC
Cog POC | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B
Knowledge Acquisition Phase ( KA ) - Week 4
Date | 2020-05-18 |  | 2020-05-19 |  | 2020-05-20 |  | 2020-05-21 |  | 2020-05-22
DAY | 17 |  | 18 |  | 19 |  | 20 |  | 21
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Time
Topic 1 | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Local Fund Agent management | Local Fund Agent management | Local Fund Agent management | Local Fund Agent management | Master Data management | Master Data management | Master Data management | Master Data management
Module Complexity | MED | MED | MED | MED | MED | MED | MED | MED | MED | MED
IBM POC
TGF POC
Cog POC | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A
Topic 2 | Investment Management (Lightning) | Investment Management (Lightning) | SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit] | Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit] | Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit] | Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit]
IBM POC
TGF POC
Cog POC | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B
Topic 3 | None | Automation Testing Overview and Test Scripts | None | Regression Testing Suite overview | None | Regression Testing Suite overview | None | Regression Testing Suite overview | None | Regression Testing Suite overview
IBM POC
TGF POC
Cog POC | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C
Topic 4 | None | Understanding of Release Management & Release Calendar | None | Understanding of Deployment Management ( Application & Salesforce Feature Release ) | None | Understanding of Deployment Management ( Application & Salesforce Feature Release ) | None | Understanding of Deployment Management ( Application & Salesforce Feature Release ) | None | Understanding of Deployment Management ( Application & Salesforce Feature Release )
IBM POC
TGF POC
Cog POC | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D
Knowledge Acquisition Phase ( KA ) - Week 5
Date | 2020-05-25 |  | 2020-05-26 |  | 2020-05-27 |  | 2020-05-28 |  | 2020-05-29
DAY | 22 |  | 23 |  | 24 |  | 25 |  | 26
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Time
Topic 1 | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | External Audit Tracking (Lightning) | External Audit Tracking (Lightning)
Module Complexity | LOW | LOW | LOW | LOW | LOW | LOW | LOW | LOW | LOW | LOW
IBM POC
TGF POC
Cog POC | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Team A | Full Team | Full Team
Topic 2 | Investment Management (Lightning) | Investment Management (Lightning) | Investment Management (Lightning) | Investment Management (Lightning) | Recoveries Management [GLCP – Recoveries] | Recoveries Management [GLCP – Recoveries] | Recoveries Management [GLCP – Recoveries] | Recoveries Management [GLCP – Recoveries]
IBM POC
TGF POC
Cog POC | Team B | Team B | Team B | Team B | Team B | Team B | Team B | Team B
Topic 3 | None | PROVAR and Selenum Tool Understanding | None | PROVAR and Selenum Tool Understanding | None | PROVAR and Selenum Tool Understanding | None | PMO Toolkit review | None | PMO Toolkit review
IBM POC
TGF POC
Cog POC | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C | Team C
Topic 4 | None | Understanding of DevOps process and usage of TGF | None | Understanding of DevOps process and usage of TGF | None | Understanding of DevOps process and usage of TGF | None | Understanding of DevOps process and usage of TGF | Tools used in TGF - SonarQube , GitHub , Jenkins | Tools used in TGF - SonarQube , GitHub , Jenkins
IBM POC
TGF POC
Cog POC | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D | Team D
Knowledge Acquisition Phase ( KA ) - Week 6
Date | 2020-06-01 |  | 2020-06-02
DAY | 27 |  | 28
Session | Before Lunch | Post Lunch | Before Lunch | Post Lunch
Time
Topic | Support and Enhancement Operations KT
IBM POC
TGF POC
Cog POC | Full Team | Full Team | Full Team | Full Team
Formulas:
Before Lunch = [Before Lunch]+1

## Plan On The Page
[12 empty] | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13
# | Task Name | Duration | Owner | Status | Start Date | End Date | KT Sender | KT Receiver | Session Status (Duration - 2 Hrs )
[9 empty] | Planned | Actual | Completion % | W1 | W2 | W3 | W4 | W5 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
TGF - GOS Transition Plan
Pre-Transition Preparation Phase |  | 6 Days | COG / TGF | Completed | 2020-04-06 | 2020-04-15 | NA | NA | NA | NA | NA | bar: W1 to W2
1 | Resource identification and finalization & Others | [7 empty] | NA | NA | NA
Transition Planning Phase |  | 6 Days | COG / TGF | In Progress | 2020-04-16 | 2020-04-23 | NA | NA | NA | NA | NA | bar: W2 to W3
2 | Study existing documents and identify gaps and build Questionnaire | [7 empty] | NA | NA | NA
3 | Identify stakeholders for KT sessions and finalize transition timelines | [7 empty] | NA | NA | NA
Knowledge Acquisition Phase ( KA ) |  | 29 Days | TGF /IBM | Yet to Start | 2020-04-24 | 2020-06-03 | TGF /IBM | COG | 101 | 0 | 0% | bar: W4 to W8
4 | Overall Business Overview | 1 Day | TGF | Yet to Start | 2020-04-24 | 2020-04-24 | TGF | COG | 1 | 0 | 0%
5 | Salesforce Org - GOS Security Configuration & Management | 1 Day | IBM | Yet to Start | 2020-04-24 | 2020-04-24 | IBM | COG | 1 | 0 | 0%
High Complex modules KT Sessions |  | 12 Days | TGF /IBM | Yet to Start | 2020-04-27 | 2020-05-12 | TGF /IBM | COG | 42 | 0 | 0%
6 | GLCP - PF and budget data | 4 Days | TGF /IBM | Yet to Start | 2020-04-27 | 2020-04-30 | TGF /IBM | COG - Team A | 7 | 0 | 0%
6.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-04-27 | 2020-04-28 | TGF | COG - Team A | 3 | 0 | 0%
6.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-04-28 | 2020-04-29 | IBM | COG - Team A | 3 | 0 | 0%
6.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-04-30 | 2020-04-30 | TGF /IBM | COG - Team A | 1 | 0 | 0%
7 | Funding Request [GLCP - IMM Fund Management] | 4 Days | TGF /IBM | Yet to Start | 2020-04-27 | 2020-04-30 | TGF /IBM | COG - Team B | 7 | 0 | 0%
7.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-04-27 | 2020-04-28 | TGF | COG - Team B | 3 | 0 | 0%
7.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-04-28 | 2020-04-29 | IBM | COG - Team B | 3 | 0 | 0%
7.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-04-30 | 2020-04-30 | TGF /IBM | COG - Team B | 1 | 0 | 0%
8 | Grant Making (Lightning) | 4 Days | TGF /IBM | Yet to Start | 2020-05-01 | 2020-05-06 | TGF /IBM | COG - Team A | 7 | 0 | 0%
8.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-05-01 | 2020-05-04 | TGF | COG - Team A | 3 | 0 | 0%
8.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-05-04 | 2020-05-05 | IBM | COG - Team A | 3 | 0 | 0%
8.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-06 | 2020-05-06 | TGF /IBM | COG - Team A | 1 | 0 | 0%
9 | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | 4 Days | TGF /IBM | Yet to Start | 2020-05-01 | 2020-05-06 | TGF /IBM | COG - Team B | 7 | 0 | 0%
9.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-05-01 | 2020-05-04 | TGF | COG - Team B | 3 | 0 | 0%
9.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-05-04 | 2020-05-05 | IBM | COG - Team B | 3 | 0 | 0%
9.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-06 | 2020-05-06 | TGF /IBM | COG - Team B | 1 | 0 | 0%
10 | Annual Funding Decisions and Disbursements | 4 Days | TGF /IBM | Yet to Start | 2020-05-07 | 2020-05-12 | TGF /IBM | COG - Team A | 7 | 0 | 0%
10.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-05-07 | 2020-05-08 | TGF | COG - Team A | 3 | 0 | 0%
10.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-05-08 | 2020-05-11 | IBM | COG - Team A | 3 | 0 | 0%
10.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-12 | 2020-05-12 | TGF /IBM | COG - Team A | 1 | 0 | 0%
11 | Progress reports | 4 Days | TGF /IBM | Yet to Start | 2020-05-07 | 2020-05-12 | TGF /IBM | COG - Team B | 7 | 0 | 0%
11.1 | Business Overview - Modules Functional KT | 1.5 Days | TGF |  | 2020-05-07 | 2020-05-08 | TGF | COG - Team B | 3 | 0 | 0%
11.2 | Technical Overview - Technical KT | 1.5 Days | IBM |  | 2020-05-08 | 2020-05-11 | IBM | COG - Team B | 3 | 0 | 0%
11.3 | Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-12 | 2020-05-12 | TGF /IBM | COG - Team B | 1 | 0 | 0%
Medium Complex Modules KT transitions begin |  | 8 Days | TGF /IBM | Yet to Start | 2020-05-13 | 2020-05-22 | TGF /IBM | COG | 32 | 0 | 0%
| GLCP - Integration | 3 Days | TGF /IBM | Yet to Start | 2020-05-13 | 2020-05-14 | TGF /IBM | COG - Team A | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-13 | 2020-05-13 | TGF | COG - Team A | 2 | 0 | 0%
| Technical Overview - Technical KT | 1 Day | IBM |  | 2020-05-14 | 2020-05-14 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-14 | 2020-05-14 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| Integrated Risk Management (IRM) [GLCP – Risk] | 3 Days | TGF /IBM | Yet to Start | 2020-05-13 | 2020-05-14 | TGF /IBM | COG - Team B | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-13 | 2020-05-13 | TGF | COG - Team B | 2 | 0 | 0%
| Technical Overview - Technical KT | 1 Day | IBM |  | 2020-05-14 | 2020-05-14 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-14 | 2020-05-14 | TGF /IBM | COG - Team B | 1 | 0 | 0%
| GLCP - IMM Grant Signing Calculator [GLCP - Signing Calculator, GLCP - IMM Portfolio Financials] | 3 Days | TGF /IBM | Yet to Start | 2020-05-15 | 2020-05-18 | TGF /IBM | COG - Team A | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-15 | 2020-05-15 | TGF | COG - Team A | 2 | 0 | 0%
| Technical Overview - Technical KT | 1 Day | IBM |  | 2020-05-18 | 2020-05-18 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-18 | 2020-05-18 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| Grant Closure | 3 Days | TGF /IBM | Yet to Start | 2020-05-15 | 2020-05-18 | TGF /IBM | COG - Team B | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-15 | 2020-05-15 | TGF | COG - Team B | 2 | 0 | 0%
| Technical Overview - Technical KT | 1 Day | IBM |  | 2020-05-18 | 2020-05-18 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 1 Day | TGF /IBM |  | 2020-05-18 | 2020-05-18 | TGF /IBM | COG - Team B | 1 | 0 | 0%
| Local Fund Agent management | 2 Days | TGF /IBM | Yet to Start | 2020-05-19 | 2020-05-20 | TGF /IBM | COG - Team A | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-19 | 2020-05-19 | TGF | COG - Team A | 2 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-20 | 2020-05-20 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-20 | 2020-05-20 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | 2 Days | TGF /IBM | Yet to Start | 2020-05-19 | 2020-05-20 | TGF /IBM | COG - Team A | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-19 | 2020-05-19 | TGF | COG - Team A | 2 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-20 | 2020-05-20 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-20 | 2020-05-20 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| Master Data management | 2 Days | TGF /IBM | Yet to Start | 2020-05-21 | 2020-05-22 | TGF /IBM | COG - Team B | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-21 | 2020-05-21 | TGF | COG - Team B | 2 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-22 | 2020-05-22 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-22 | 2020-05-22 | TGF /IBM | COG - Team B | 1 | 0 | 0%
| Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit] | 2 Days | TGF /IBM | Yet to Start | 2020-05-21 | 2020-05-22 | TGF /IBM | COG - Team B | 4 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-21 | 2020-05-21 | TGF | COG - Team B | 2 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-22 | 2020-05-22 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-22 | 2020-05-22 | TGF /IBM | COG - Team B | 1 | 0 | 0%
Low Complex Modules KT transitions begin |  | 5 Days | TGF /IBM | Yet to Start | 2020-05-25 | 2020-05-29 | TGF /IBM | COG | 14 | 0 | 0%
| Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | 2 Days | TGF /IBM | Yet to Start | 2020-05-25 | 2020-05-26 | TGF /IBM | COG - Team A | 3 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-25 | 2020-05-25 | TGF | COG - Team A | 1 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-26 | 2020-05-26 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-26 | 2020-05-26 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| Investment Management (Lightning) | 2 Days | TGF /IBM | Yet to Start | 2020-05-25 | 2020-05-26 | TGF /IBM | COG - Team B | 3 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-25 | 2020-05-25 | TGF | COG - Team B | 1 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-26 | 2020-05-26 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-26 | 2020-05-26 | TGF /IBM | COG - Team B | 1 | 0 | 0%
| Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | 2 Days | TGF /IBM | Yet to Start | 2020-05-27 | 2020-05-28 | TGF /IBM | COG - Team A | 3 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-27 | 2020-05-27 | TGF | COG - Team A | 1 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-28 | 2020-05-28 | IBM | COG - Team A | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-28 | 2020-05-28 | TGF /IBM | COG - Team A | 1 | 0 | 0%
| Recoveries Management [GLCP – Recoveries] | 2 Days | TGF /IBM | Yet to Start | 2020-05-27 | 2020-05-28 | TGF /IBM | COG - Team B | 3 | 0 | 0%
| Business Overview - Modules Functional KT | 1 Day | TGF |  | 2020-05-27 | 2020-05-27 | TGF | COG - Team B | 1 | 0 | 0%
| Technical Overview - Technical KT | 0.5 Days | IBM |  | 2020-05-28 | 2020-05-28 | IBM | COG - Team B | 1 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.5 Days | TGF /IBM |  | 2020-05-28 | 2020-05-28 | TGF /IBM | COG - Team B | 1 | 0 | 0%
| External Audit Tracking (Lightning) | 1 Days | TGF /IBM | Yet to Start | 2020-05-29 | 2020-05-29 | TGF /IBM | COG - Team B | 2 | 0 | 0%
| Business Overview - Modules Functional KT | 0.3 Days | TGF |  | 2020-05-29 | 2020-05-29 | TGF | COG - Team B | 1 | 0 | 0%
| Technical Overview - Technical KT | 0.3 Days | IBM |  | 2020-05-29 | 2020-05-29 | IBM | COG - Team B | 0.5 | 0 | 0%
| Module Level - Issues & Known Error Overview | 0.3 Days | TGF /IBM |  | 2020-05-29 | 2020-05-29 | TGF /IBM | COG - Team B | 0.5 | 0 | 0%
Grant Operating System (GOS) - QA Process & Tool KT |  | 10 Days | TGF /IBM | Yet to Start | 2020-05-18 | 2020-05-29 | TGF /IBM | COG - Team C | 10 | 0 | 0%
| Automation Testing Overview and Test Scripts | 1 Days |  |  | 2020-05-18 | 2020-05-18 | IBM - Testing | COG - Team C | 1 | 0 | 0%
| Regression Testing Suite overview | 4 Days |  |  | 2020-05-19 | 2020-05-22 | IBM - Testing | COG - Team C | 4 | 0 | 0%
| PROVAR and Selenum Tool Understanding | 4 Days |  |  | 2020-05-25 | 2020-05-28 | IBM - Testing | COG - Team C | 4 | 0 | 0%
| PMO Toolkit review | 1 Days |  |  | 2020-05-29 | 2020-05-29 | IBM - Testing | COG - Team C | 1 | 0 | 0%
Grant Operating System (GOS) - DevOps KT |  | 10 Days | TGF /IBM | Yet to Start | 2020-05-18 | 2020-05-29 | TGF /IBM | COG - Team D | 10 | 0 | 0%
| Understanding of Release & Deployment Management | 1 Days |  |  | 2020-05-18 | 2020-05-18 | IBM - DevOps | COG - Team D | 1 | 0 | 0%
| Understanding of Deployment Management ( Application & Salesforce Feature Release ) | 4 Days |  |  | 2020-05-19 | 2020-05-22 | IBM - DevOps | COG - Team D | 4 | 0 | 0%
| Understanding of DevOps process and usage of TGF | 4 Days |  |  | 2020-05-25 | 2020-05-28 | IBM - DevOps | COG - Team D | 4 | 0 | 0%
| Tools used in TGF - SonarQube , GitHub , Jenkins | 1 Days |  |  | 2020-05-29 | 2020-05-29 | IBM - DevOps | COG - Team D | 1 | 0 | 0%
Support and Enhancement Operations KT |  | 2 Days | TGF /IBM | Yet to Start | 2020-06-01 | 2020-06-02 | TGF /IBM | COG | 4 | 0 | 0%
| Application Support Schedule & Communication Plan | 0.5 Days |  |  | 2020-06-01 | 2020-06-01 | TGF /IBM | COG | 1 | 0 | 0%
| Ticketing Process & Details | 1 Days |  |  | 2020-06-02 | 2020-06-02 | TGF /IBM | COG | 2 | 0 | 0%
| Environment Management KT | 0.5 Days |  |  | 2020-06-02 | 2020-06-02 | TGF /IBM | COG | 1 | 0 | 0%
Reverse KT sessions with TGF SME & Incumbent team |  | 1 Days | TGF /IBM/COG | Yet to Start | 2020-06-03 | 2020-06-03 | COG | TGF /IBM | 4 | 0 | 0%
Assessment and Review with TGF SME |  | 1 Days | TGF /IBM | Yet to Start | 2020-06-03 | 2020-06-03 | TGF /IBM | COG | NA | NA | NA
Shadow Phase ( SH ) |  | 15 Days | TGF /IBM /COG | Yet to Start | 2020-06-04 | 2020-06-24 | TGF /IBM | COG | 45 | 0 | 0% | bar: W9 to W11
| Observe & monitor incumbent support team |  |  |  | 2020-06-04 | 2020-06-24
| Resolve Incidents and SR's under watch of existing support team | 15 Days |  |  | 2020-06-04 | 2020-06-24 | TGF /IBM | COG - Team A&B | 30 | 0 | 0%
| Resolve Incidents and SR's under watch of existing support team - QA Track | 15 Days |  |  | 2020-06-04 | 2020-06-24 | TGF /IBM Testing SME | COG - TeamC | 15 | 0 | 0%
| Ticket Baselining and addressing Open Backlogs |  |  |  | 2020-06-04 | 2020-06-24
| Formalize the communication approach/medium |  |  |  | 2020-06-04 | 2020-06-24
| Assess - Gating Criteria |  |  |  | 2020-06-04 | 2020-06-24 | TGF | COG
Reverse -Shadow Phase ( RH ) |  | 15 Days | TGF /IBM /COG | Yet to Start | 2020-06-25 | 2020-07-15 | COG | TGF /IBM | 20 | 0 | 0% | bar: W12 to W14
| Assume primary support for Incidents and SR's - SF & QA | 15 Days |  |  | 2020-06-25 | 2020-07-15 | COG | TGF /IBM SF / IBM Testing SME | 20 | 0 | 0%
| SOP creation and update |  |  |  | 2020-06-25 | 2020-07-15 | COG | TGF /IBM SF / IBM Testing SME
| Finalize KPI's and Metrics |  |  |  | 2020-06-25 | 2020-07-15 | COG | TGF /IBM SF / IBM Testing SME
| Assess - Gating Criteria |  |  |  | 2020-06-25 | 2020-07-15 | COG | TGF /IBM SF / IBM Testing SME
| Transition exit sign-off |  |  |  | 2020-06-25 | 2020-07-15 | COG | TGF /IBM SF / IBM Testing SME
Transition Goverance & Tracking |  | 59 Days | TGF /IBM /COG | Yet to Start | 2020-04-24 | 2020-07-15 | COG | TGF /IBM | NA | NA | NA | W1: KA Goverance & Tracking
| KT Progress Tracking and Status Reporting |  |  |  | 2020-04-24 | 2020-07-15 | COG | TGF
*************** END OF PLAN **************
Formulas:
Start Date = [Start Date, row above]
We're Here

## Detailed Plan
Sl.No | Phases | Owner | Status | Dependency | Location | Duration in Days | Session ( Duration 2 Hrs ) | Start Date | End Date | KT Sender | KT Receiver | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15
 | time axis 2020-04-06 to 2020-07-15
1 | Pre-Transition Preparation | [6 empty] | 2020-04-06 | 2020-04-22 | bar: 2020-04-06 to 2020-04-22
1.1 | Resource identification and finalization | Velu | In Progress |  | India |  |  | 2020-04-06 | 2020-04-17 | bar: 2020-04-06 to 2020-04-17
1.2 | Finalize the access needs for Cognizant team (SNOW, GOS, Sandboxes, TGF id) | Irina | Pending |  | India |  |  | 2020-04-08 | 2020-04-16 | bar: 2020-04-08 to 2020-04-16
1.3 | Raise requests for access & Track the status of Access requests | Velu | Pending |  | India |  |  | 2020-04-13 | 2020-04-16 | bar: 2020-04-13 to 2020-04-16
1.4 | Setup Connectivity to environment (existing Salesforce Applications and tool access) |  | Pending | 1.3 | India |  |  | 2020-04-15 | 2020-04-22 | bar: 2020-04-15 to 2020-04-22
1.5 | Walkthough of existing Application landscape, Current Incident Mgmt. & Change Mgmt. processes and Communication templates being followed with current AMS Team | Velu | In Progress |  | India |  |  | 2020-04-13 | 2020-04-17 | bar: 2020-04-13 to 2020-04-17
1.6 | KT plan for additional resources - Onboarding process | Pallab / DC | Pending |  | India |  |  | 2020-04-13 | 2020-04-12 | bar: 2020-04-13 to 2020-04-17
1.7 | Arrange travel logistics and finalize travel plans |  |  |  | India
2 | Transition Planning Phase | [6 empty] | 2020-04-07 | 2020-04-23 | bar: 2020-04-07 to 2020-04-23
2.1 | Collect existing documents (Application Design docs, Process Maps, Support Process documents etc.) | DC | Pending |  | India/Remote |  |  | 2020-04-13 | 2020-04-21 | bar: 2020-04-13 to 2020-04-21
2.2 | Study existing documents and identify gaps and build Questionnaire | Velu | Pending | 2.1 | India/Remote |  |  | 2020-04-07 | 2020-04-23 | bar: 2020-04-07 to 2020-04-23
2.3 | Identify stakeholders for KT sessions | DC | Pending |  | India/Remote |  |  | 2020-04-19 | 2020-04-20 | bar: 2020-04-20 to 2020-04-21
2.4 | Block calendars | DC | Pending | 2.3 | India/Remote |  |  | 2020-04-21 | 2020-04-23 | bar: 2020-04-22 to 2020-04-23
2.5 | Finalize KT templates and Identify entry/exit criteria for all the phases | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-16 | 2020-04-23 | bar: 2020-04-16 to 2020-04-23
2.6 | Finalize Transition Timelines | Velu / DC | Pending | 2.4, 2.5 | India/Remote |  |  | 2020-04-16 | 2020-04-21 | bar: 2020-04-16 to 2020-04-23
2.7 | GOS Org Assessment | Velu / DC | Pending | 1.2 | India/Remote |  |  | 2020-04-16 | 2020-04-23 | bar: 2020-04-16 to 2020-04-23
2.8 | Milestone : KT Plan Sign-off |  |  | 2.6 | -
| Knowledge Acquisition Phase Begins |  |  |  |  | 29 |  | 2020-04-24 | 2020-06-03 | bar: 2020-04-24 to 2020-06-03
3 | Functional & Technical KT - Grant Operating System (GOS) | bar: 2020-04-24 to 2020-05-20
3.1 | Overall Business Overview | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
3.2 | Salesforce Org - GOS Security Configuration & Management | Velu / DC |  |  |  | 1 | 1 | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| Security Controls | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| Access restriction - IP Level | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| Profile and Permission Set for Org and ServiceMax Application Level | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| OWD- High level for Org and ServiceMax Application Level | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| Salesforce Org Hierarchy | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
| SSO Setup Detail Walkthrough, if any | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-24 | 2020-04-24 | TGF SME | Full Team | bar: 2020-04-24
3.3 | High Complex Modules KT transitions begin | Velu / DC | Pending |  | India/Remote | 12 |  | 2020-04-27 | 2020-05-12 | bar: 2020-04-27 to 2020-05-12
3.3.1 | GLCP - PF and budget data | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-04-27 | 2020-04-30 | bar: 2020-04-27 to 2020-04-30
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-04-27 | 2020-04-28 | TGF SME | Team A | bar: 2020-04-27 to 2020-04-30
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team A | bar: 2020-04-27 to 2020-04-30
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team A | bar: 2020-04-27 to 2020-04-30
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team A | bar: 2020-04-27 to 2020-04-30
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team A | bar: 2020-04-27 to 2020-04-30
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team A | bar: 2020-04-27 to 2020-04-30
3.3.2 | Funding Request [GLCP - IMM Fund Management] | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-04-27 | 2020-04-30 | bar: 2020-04-27 to 2020-04-30
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-04-27 | 2020-04-28 | TGF SME | Team B | bar: 2020-04-27 to 2020-04-30
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team B | bar: 2020-04-27 to 2020-04-30
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team B | bar: 2020-04-27 to 2020-04-30
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team B | bar: 2020-04-27 to 2020-04-30
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-27 | 2020-04-28 | TGF SME | Team B | bar: 2020-04-27 to 2020-04-30
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-28 | 2020-04-29 | IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-04-30 | 2020-04-30 | TGF/ IBM SME | Team B | bar: 2020-04-27 to 2020-04-30
3.3.3 | Grant Making (Lightning) | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-05-01 | 2020-05-06 | bar: 2020-05-01 to 2020-05-06
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-05-01 | 2020-05-04 | TGF SME | Team A | bar: 2020-05-01 to 2020-05-06
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team A | bar: 2020-05-01 to 2020-05-06
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team A | bar: 2020-05-01 to 2020-05-06
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team A | bar: 2020-05-01 to 2020-05-06
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team A | bar: 2020-05-01 to 2020-05-06
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team A | bar: 2020-05-01 to 2020-05-06
3.3.4 | Grant Revisions [GOS – Imports, Salesforce - Data Loader] | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-05-01 | 2020-05-06 | bar: 2020-05-01 to 2020-05-06
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-05-01 | 2020-05-04 | TGF SME | Team B | bar: 2020-05-01 to 2020-05-06
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team B | bar: 2020-05-01 to 2020-05-06
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team B | bar: 2020-05-01 to 2020-05-06
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team B | bar: 2020-05-01 to 2020-05-06
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-01 | 2020-05-04 | TGF SME | Team B | bar: 2020-05-01 to 2020-05-06
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-04 | 2020-05-05 | IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-06 | 2020-05-06 | TGF/ IBM SME | Team B | bar: 2020-05-01 to 2020-05-06
3.3.5 | Annual Funding Decisions and Disbursements | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-05-07 | 2020-05-12 | bar: 2020-05-07 to 2020-05-12
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-05-07 | 2020-05-08 | TGF SME | Team A | bar: 2020-05-07 to 2020-05-12
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team A | bar: 2020-05-07 to 2020-05-12
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team A | bar: 2020-05-07 to 2020-05-12
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team A | bar: 2020-05-07 to 2020-05-12
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team A | bar: 2020-05-07 to 2020-05-12
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team A | bar: 2020-05-07 to 2020-05-12
3.3.6 | Progress reports | Velu / DC | Pending |  | India/Remote | 4 |  | 2020-05-07 | 2020-05-12 | bar: 2020-05-07 to 2020-05-12
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 1.5 | 3 | 2020-05-07 | 2020-05-08 | TGF SME | Team B | bar: 2020-05-07 to 2020-05-12
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team B | bar: 2020-05-07 to 2020-05-12
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team B | bar: 2020-05-07 to 2020-05-12
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team B | bar: 2020-05-07 to 2020-05-12
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-07 | 2020-05-08 | TGF SME | Team B | bar: 2020-05-07 to 2020-05-12
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 1.5 | 3 | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | [5 empty] | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-08 | 2020-05-11 | IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 1 | 1 | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-12 | 2020-05-12 | TGF/ IBM SME | Team B | bar: 2020-05-07 to 2020-05-12
3.4 | Medium Complex Modules KT transitions begin | Velu / DC | Pending |  | India/Remote | 8 |  | 2020-05-13 | 2020-05-22 | bar: 2020-05-13 to 2020-05-22
3.4.1 | GLCP - Integration | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-13 | 2020-05-14 | bar: 2020-05-13 to 2020-05-14
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-13 | 2020-05-13 | TGF SME | Team A | bar: 2020-05-13 to 2020-05-14
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team A | bar: 2020-05-13 to 2020-05-14
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team A | bar: 2020-05-13 to 2020-05-14
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team A | bar: 2020-05-13 to 2020-05-14
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team A | bar: 2020-05-13 to 2020-05-14
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-14 | 2020-05-14 | IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team A | bar: 2020-05-13 to 2020-05-14
3.4.2 | Integrated Risk Management (IRM) [GLCP – Risk] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-13 | 2020-05-14 | bar: 2020-05-13 to 2020-05-14
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-13 | 2020-05-13 | TGF SME | Team B | bar: 2020-05-13 to 2020-05-14
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team B | bar: 2020-05-13 to 2020-05-14
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team B | bar: 2020-05-13 to 2020-05-14
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team B | bar: 2020-05-13 to 2020-05-14
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-13 | 2020-05-13 | TGF SME | Team B | bar: 2020-05-13 to 2020-05-14
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-14 | 2020-05-14 | TGF/ IBM SME | Team B | bar: 2020-05-13 to 2020-05-14
3.4.3 | GLCP - IMM Grant Signing Calculator [GLCP - Signing Calculator, GLCP - IMM Portfolio Financials] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-15 | 2020-05-18 | bar: 2020-05-15 to 2020-05-18
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-15 | 2020-05-15 | TGF SME | Team A | bar: 2020-05-15 to 2020-05-18
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team A | bar: 2020-05-15 to 2020-05-18
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team A | bar: 2020-05-15 to 2020-05-18
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team A | bar: 2020-05-15 to 2020-05-18
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team A | bar: 2020-05-15 to 2020-05-18
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team A | bar: 2020-05-15 to 2020-05-18
3.4.4 | Grant Closure | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-15 | 2020-05-18 | bar: 2020-05-15 to 2020-05-18
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-15 | 2020-05-15 | TGF SME | Team B | bar: 2020-05-15 to 2020-05-18
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team B | bar: 2020-05-15 to 2020-05-18
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team B | bar: 2020-05-15 to 2020-05-18
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team B | bar: 2020-05-15 to 2020-05-18
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-15 | 2020-05-15 | TGF SME | Team B | bar: 2020-05-15 to 2020-05-18
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-18 | 2020-05-18 | TGF/ IBM SME | Team B | bar: 2020-05-15 to 2020-05-18
3.4.5 | Local Fund Agent management | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-19 | 2020-05-20 | bar: 2020-05-19 to 2020-05-20
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
3.4.6 | SIP [GLCP – Strategic Information] & Sourcing Tool [Salesforce - Performance & Accountability Tracker (P&A Tracker), Salesforce - Procurement KPI Dashboard] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-19 | 2020-05-20 | bar: 2020-05-19 to 2020-05-20
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-19 | 2020-05-19 | TGF SME | Team A | bar: 2020-05-19 to 2020-05-20
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-20 | 2020-05-20 | TGF/ IBM SME | Team A | bar: 2020-05-19 to 2020-05-20
3.4.7 | Master Data management | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-21 | 2020-05-22 | bar: 2020-05-21 to 2020-05-22
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Technical Overview - Technical KT | Velu / DC |  |  |  | 0.5 | 1 | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | [5 empty] | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
3.4.8 | Distributor List Mgmt & External Provisioning [Salesforce - Access,wambo.org,Openshare Portal, PET,Approval Cockpit] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-21 | 2020-05-22 | bar: 2020-05-21 to 2020-05-22
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 2 | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-21 | 2020-05-21 | TGF SME | Team B | bar: 2020-05-21 to 2020-05-22
| Technical Overview - Technical KT | Velu / DC |  |  |  | 0.5 | 1 | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | [5 empty] | 2020-05-22 | 2020-05-22 | IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-22 | 2020-05-22 | TGF/ IBM SME | Team B | bar: 2020-05-21 to 2020-05-22
3.5 | Low Complex Modules KT transitions begin | Velu / DC | Pending |  | India/Remote | 5 |  | 2020-05-25 | 2020-05-29 | bar: 2020-05-25 to 2020-05-29
3.5.1 | Grant Implementation [GLCP - Quarterly Cash Balance Report,GLCP - Tax Report] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-25 | 2020-05-26 | bar: 2020-05-25 to 2020-05-26
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-25 | 2020-05-25 | TGF SME | Team A | bar: 2020-05-25 to 2020-05-26
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team A | bar: 2020-05-25 to 2020-05-26
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team A | bar: 2020-05-25 to 2020-05-26
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team A | bar: 2020-05-25 to 2020-05-26
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team A | bar: 2020-05-25 to 2020-05-26
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team A | bar: 2020-05-25 to 2020-05-26
3.5.2 | Investment Management (Lightning) | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-25 | 2020-05-26 | bar: 2020-05-25 to 2020-05-26
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-25 | 2020-05-25 | TGF SME | Team B | bar: 2020-05-25 to 2020-05-26
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team B | bar: 2020-05-25 to 2020-05-26
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team B | bar: 2020-05-25 to 2020-05-26
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team B | bar: 2020-05-25 to 2020-05-26
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-25 | 2020-05-25 | TGF SME | Team B | bar: 2020-05-25 to 2020-05-26
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-26 | 2020-05-26 | TGF/ IBM SME | Team B | bar: 2020-05-25 to 2020-05-26
3.5.3 | Financial Management Impact Review (Lightning) [GLCP – Financial Risk Management] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-27 | 2020-05-28 | bar: 2020-05-27 to 2020-05-28
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-27 | 2020-05-27 | TGF SME | Team A | bar: 2020-05-27 to 2020-05-28
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team A | bar: 2020-05-27 to 2020-05-28
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team A | bar: 2020-05-27 to 2020-05-28
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team A | bar: 2020-05-27 to 2020-05-28
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team A | bar: 2020-05-27 to 2020-05-28
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team A | bar: 2020-05-27 to 2020-05-28
3.5.4 | Recoveries Management [GLCP – Recoveries] | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-05-27 | 2020-05-28 | bar: 2020-05-27 to 2020-05-28
| Business Overview - Modules Functional KT | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-27 | 2020-05-27 | TGF SME | Team B | bar: 2020-05-27 to 2020-05-28
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team B | bar: 2020-05-27 to 2020-05-28
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team B | bar: 2020-05-27 to 2020-05-28
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team B | bar: 2020-05-27 to 2020-05-28
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-27 | 2020-05-27 | TGF SME | Team B | bar: 2020-05-27 to 2020-05-28
| Technical Overview - Technical KT | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Module Level - Issues & Known Error Overview | Velu / DC | Pending |  | India/Remote | 0.5 | 1 | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-28 | 2020-05-28 | TGF/ IBM SME | Team B | bar: 2020-05-27 to 2020-05-28
3.5.5 | External Audit Tracking (Lightning) | Velu / DC | Pending |  | India/Remote | 1 |  | 2020-05-29 | 2020-05-29 | bar: 2020-05-29
| Business Overview - Modules Functional KT | Velu / DC |  |  |  | 0.3 | 1 | 2020-05-29 | 2020-05-29 | TGF SME | Team A | bar: 2020-05-29
| Business function of application - E2E Functional Architecure | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF SME | Team A | bar: 2020-05-29
| Business process Flow - By Business Persona | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF SME | Team A | bar: 2020-05-29
| Integration touchpoints - Functional Overview (Others) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF SME | Team A | bar: 2020-05-29
| Known Errors and Issues & Others | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF SME | Team A | bar: 2020-05-29
| Technical Overview - Technical KT | Velu / DC |  |  |  | 0.3 | 1 | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Data model walkthrough (Standard & Custom Objects) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Module Setup & Configurations Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Module Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Module Settings Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Integration Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Batch Jobs Customization Overview | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| AppExchange Tool Detail Walkthrough - Apttus X-Author / Conga / Adobe e-sign / Gridbuddy | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Salesforce Community Cloud - Detail Walkthrough ( If Applicable ) | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Detail Code Walkthrough - Covers SonarQube Level Gating Criteria with BestPractice | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | IBM SME | Team A | bar: 2020-05-29
| Module Level - Issues & Known Error Overview | Velu / DC |  |  |  | 0.3 | 1 | 2020-05-29 | 2020-05-29 | TGF/ IBM SME | Team A | bar: 2020-05-29
| Current Challenges/Pain areas/ Areas of improvement in the project | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF/ IBM SME | Team A | bar: 2020-05-29
| Recently raised Defect/Incident walkthrough along with resolutions | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF/ IBM SME | Team A | bar: 2020-05-29
| Frequently Occurring Issues& Remedies | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF/ IBM SME | Team A | bar: 2020-05-29
| Walk through of the recent changes that has been implemented | Velu / DC | Pending |  | India/Remote |  |  | 2020-05-29 | 2020-05-29 | TGF/ IBM SME | Team A | bar: 2020-05-29
3.6 | Grant Operating System (GOS) - QA Process & Tool KT | Velu / DC | Pending |  | India/Remote | 10 |  | 2020-05-18 | 2020-05-29 | bar: 2020-05-18 to 2020-05-29
| Automation Testing Overview and Test Scripts | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-18 | 2020-05-18 | IBM Testing SME | Team C | bar: 2020-05-18 to 2020-05-21
| Regression Testing Suite overview | Velu / DC | Pending |  | India/Remote | 4 | 4 | 2020-05-19 | 2020-05-22 | IBM Testing SME | Team C | bar: 2020-05-20 to 2020-05-25
| PROVAR and Selenum Tool Understanding | Velu / DC | Pending |  | India/Remote | 4 | 4 | 2020-05-25 | 2020-05-28 | IBM Testing SME | Team C | bar: 2020-05-25 to 2020-05-28
| PMO Toolkit review | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-29 | 2020-05-29 | IBM Testing SME | Team C | bar: 2020-05-29
3.7 | Grant Operating System (GOS) - DevOps KT | Velu / DC | Pending |  | India/Remote | 10 |  | 2020-05-18 | 2020-05-29 | bar: 2020-05-18 to 2020-05-29
| Understanding of Release Management & Release Calendar | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-18 | 2020-05-18 | IBM DevOps SME | Team D | bar: 2020-05-18 to 2020-05-21
| Understanding of Deployment Management ( Application & Salesforce Feature Release ) | Velu / DC | Pending |  | India/Remote | 4 | 4 | 2020-05-19 | 2020-05-22 | IBM DevOps SME | Team D | bar: 2020-05-20 to 2020-05-25
| Understanding of DevOps process and usage of TGF | Velu / DC | Pending |  | India/Remote | 4 | 4 | 2020-05-25 | 2020-05-28 | IBM DevOps SME | Team D | bar: 2020-05-25 to 2020-05-28
| Tools used in TGF - SonarQube , GitHub , Jenkins | Velu / DC | Pending |  | India/Remote | 1 | 1 | 2020-05-29 | 2020-05-29 | IBM DevOps SME | Team D | bar: 2020-05-29
3.8 | Support and Enhancement Operations KT | Velu / DC | Pending |  | India/Remote | 2 |  | 2020-06-01 | 2020-06-02 | bar: 2020-06-01 to 2020-06-03
| Application Support Schedule & Communication Plan | Velu / DC |  |  |  | 0.5 | 1 | 2020-06-01 | 2020-06-01 | TGF/ IBM SME | Full Team
| Collation of stake holder information and Communication Process with Various Stakeholders | Velu / DC | Pending |  | India/Remote |  |  | 2020-06-01 | 2020-06-01 | TGF/ IBM SME | Full Team
| Support Schedule | Velu / DC | Pending |  | India/Remote |  |  | 2020-06-01 | 2020-06-01 | TGF/ IBM SME | Full Team
| Routine maintenance activities involved | Velu / DC | Pending |  | India/Remote |  |  | 2020-06-01 | 2020-06-01 | TGF/ IBM SME | Full Team
| Ticketing Process & Details | Velu / DC |  |  |  | 1 | 2 | 2020-06-01 | 2020-06-02
| Understanding of Incident Management | Velu / DC | Pending |  | India/Remote |  | 1 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding of Problem Management | Velu / DC | Pending |  | India/Remote |  | 1 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding of Change Management / Break Fix | Velu / DC | Pending |  | India/Remote |  | 1 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding of Configuration Management | Velu / DC | Pending |  | India/Remote |  | 1 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding of Release& Deployment Management ( Application & Salesforce Feature Release ) - CI / CD process | Velu / DC | Pending |  | India/Remote |  | 2 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding of Outage Planning / Business Continuity plan / Salesforce Backup Strategy /Disaster Recovery Plan | Velu / DC | Pending |  | India/Remote |  | 2 | 2020-06-01 | 2020-06-02 | IBM SME | Full Team
| Understanding Monthly and Yearly Salesforce Business process ( If any) | Velu / DC | Pending |  | India/Remote |  | 2 | 2020-06-01 | 2020-06-02 | TGF SME | Full Team
| Understanding Regulatory compliance Specific Process ( e.g. SOX Process) | Velu / DC | Pending |  | India/Remote |  | 2 | 2020-06-01 | 2020-06-02 | TGF SME | Full Team
3.8 | Environment Management KT | Velu / DC |  |  |  | 0.5 | 1 | 2020-06-02 | 2020-06-02
| Configuration Management Process Understanding | Velu / DC | Pending |  | India/Remote |  | 3 | 2020-06-02 | 2020-06-02 | IBM SME | Full Team
| Understanding of Release Management | Velu / DC | Pending |  | India/Remote |  | 3 | 2020-06-02 | 2020-06-02 | IBM SME | Full Team
| Tool Overview : SonarQube, GitHub, Jenkins etc. | Velu / DC | Pending |  | India/Remote |  | 3 | 2020-06-02 | 2020-06-02 | IBM SME | Full Team
3.9 | Reverse KT sessions with TGF SME & Incumbent team | Velu / DC | Pending |  | India/Remote | 1 | 3 | 2020-06-03 | 2020-06-03 | TGF SME | Full Team
| Assessment and Review with TGF SME | Velu / DC | Pending |  | India/Remote | 1 |  | 2020-06-03 | 2020-06-03 | TGF SME | Full Team
4 | Secondary Support (Shadow) Phase |  |  |  |  | 15 |  | 2020-06-04 | 2020-06-24 | TGF/ IBM SME | Full Team | bar: 2020-06-04 to 2020-06-24
4.1 | Observe & monitor incumbent support team | TBD | Pending |  | India + Geneva |  |  | 2020-06-04 | 2020-06-24 | bar: 2020-06-04 to 2020-06-24
4.2 | Resolve Incidents and SR's under watch of existing support team | TBD | Pending |  | India + Geneva | 15 | 30 | 2020-06-04 | 2020-06-24 | IBM SME | Cog Team A & B | bar: 2020-06-04 to 2020-06-24
4.2 | Resolve Incidents and SR's under watch of existing support team - QA Track | TBD | Pending |  | India + Geneva | 15 | 15 | 2020-06-04 | 2020-06-24 | IBM Testing SME | Cog Team C | bar: 2020-06-04 to 2020-06-24
4.3 | Ticket Baselining and addressing Open Backlogs | TBD | Pending |  | India + Geneva |  |  | 2020-06-04 | 2020-06-24 | bar: 2020-06-04 to 2020-06-24
4.4 | Formalize the communication approach/medium | TBD | Pending |  | India + Geneva |  |  | 2020-06-04 | 2020-06-24 | bar: 2020-06-04 to 2020-06-24
5 | Primary Support (Reverse Shadow) Phase |  |  |  |  | 15 |  | 2020-06-25 | 2020-07-15 | TGF/ IBM SME | Full Team | bar: 2020-06-25 to 2020-07-15
5.1 | Assume primary support for Incidents and SR's | TBD | Pending |  | India + Geneva | 15 | 20 | 2020-06-25 | 2020-07-15 | IBM SME | Cog Team A & B | bar: 2020-06-25 to 2020-07-15
5.2 | SOP creation and update | TBD | Pending |  | India + Geneva | 15 |  | 2020-06-25 | 2020-07-15 | IBM Testing SME | Cog Team C | bar: 2020-06-25 to 2020-07-15
5.3 | Finalize KPI's and Metrics | TBD | Pending |  | India + Geneva |  |  | 2020-06-25 | 2020-07-15 | bar: 2020-06-25 to 2020-07-15
5.4 | Transition exit sign-off | TBD | Pending |  | Geneva |  |  | 2020-06-25 | 2020-07-15
| KT Progress Tracking and Status Reporting |  |  |  | -

## Team Structure
Proposed Run Team Structure - GOS
3
Executive Sponsor
Client Partner
(Mohit Sawant)
SFDC Transition Director
(Pallab Mukherjee)
Service Support Manager
Business SMEs, Application Owners
SFDC Lead BA
( Yet to be Identified )
Service Delivery Manager
( Yet to be Identified )
SFDC Lead & Offshore Manager
( Ganesh Subbiah )
Steering
Committee
Service
Management
Office
Service Support
Team
SFDC Technical Analyst
( Yet to be Identified )
SFDC Practice Head
(Vibhor Singh)
SFDC Support & QA Analysts (3)
(Padmanaban)
(Yet to Identified)
(Yet to Identified)
The Global Fund
Cognizant Onsite (Geneva)
Cognizant Offshore (India - Chennai)
SFDC Sr.Support Analyst
(2)
( Ragavendra )
(Yet to Identified)
SFDC Sr. Salesforce Specialist
(Kumaravel Mathivanan )
SFDC Techno-Functional Consultant
( Uma Maheswari )
Cognizant Onshore
Cognizant Offshore
Cognizant Onshore / Offshore
Client Partner, SFDC Practice Partner and SFDC Delivery Director and Transition Director roles are investments by Cognizant
SFDC Delivery Director
( Velumani Angappan )

## Internal - Ticket Volume Calc
Allocation & Program Split | Topics | Ticket count in last 12 months | Module Complexity
• Grant Implementation, including: | Grant Allocation Management | 129 | Low
• Investment Management (Lightning) | Investment Management | 190 | Low
• Financial Management Impact Review (Lightning) | Financial Risk & Assurance | 199 | Low
GLCP - PF and budget data | Funding Request Management | 224 | High
GLCP - Integration |  | 240 | Medium
• Funding Request | Funding Request Management | 250 | High
• Integrated Risk Management (IRM) | Financial Risk & Assurance | 461 | Medium
GLCP - IMM Grant Signing Calculator | Grant Making and Revision | 549 | Medium
• Recoveries Management | Recoveries, UQD/PAAR and Differentiation | 793 | Low
• External Audit Tracking (Lightning) | Distribution List Management & External User Provisioning | 895 | Low
• Grant Making (Lightning) | Grant Making and Revision | 978 | High
• Grant Closure | Grant Disbursement & Closure | 1130 | Medium
• Local Fund Agent management | Funding Request Management | 1594 | Medium
• Grant Revisions | Grant Making and Revision | 1840 | High
• Annual Funding Decisions and Disbursements | Funding Request Management | 2826 | High
• Progress reports | Procurement KPI Reporting (Sourcing Portal) | 2980 | High
• Master Data management | Master Data Management | 5106 | Medium
Total |  | 20384
GLCP - PF and budget data | 3 |  | 13
• Funding Request |  |  |  | 30
• Grant Making (Lightning)
• Grant Revisions
• Annual Funding Decisions and Disbursements
• Progress reports
GLCP - Integration | 2 |  | 8
• Integrated Risk Management (IRM)
GLCP - IMM Grant Signing Calculator
• Grant Closure
• Local Fund Agent management
• Master Data management
• Grant Implementation, including: | 1 |  | 5
• Investment Management (Lightning)
• Financial Management Impact Review (Lightning)
• Recoveries Management
• External Audit Tracking (Lightning)
| others |  | 3

## Knowledge Acquisition Details
Knowledge Acquisition Pillars | Incumbent Vendor PoC | Cognizant PoC | TGF PoC | No. of Days | Planned Hours/day | Total Hrs. Planned | To be filled after the KT session
[7 empty] | Session Completed Date | Session Completed Time (CET) | Attendees TGF | Attendees IBM | Attendees Cognizant | % complete | RAG | Issues/ Risks | Recording Uploaded (Y/N) | Follow up Needed (Y/N) | Remarks | Planned No of Hours | Completed No of Hours | Remarks TGF
Application Functional KT
Overall Application Landscape
Overview of Application landscape including Salesforce ecosystem and Integration with GFS, SharePoint, WorkDay, BI and other systems via DataHub | TBD | TBD | TBD | 2 | 4 | 8
Grant Operating System (GOS) |  |  |  | 6 | 4 | 24
Grant Allocation Management | TBD | TBD | TBD | 1 | 4 | 4
Grant Making and Revision | TBD | TBD | TBD | 1 | 4 | 4
Funding Request Management | TBD | TBD | TBD | 1 | 3 | 3
Investment Management | TBD | TBD | TBD | 1 | 2 | 2
Portfolio Management | TBD | TBD | TBD | 1 | 2 | 2
LFA Management | TBD | TBD | TBD | 1 | 1 | 1
Grant Disbursement & Closure | TBD | TBD | TBD | 1 | 2 | 2
Financial Risk & Assurance | TBD | TBD | TBD | 1 | 2 | 2
Master Data Management | TBD | TBD | TBD | 1 | 2 | 2
Recoveries, UQD/PAAR and Differentiation | TBD | TBD | TBD | 1 | 2 | 2
Strategy Implementation Plan Tracker (SIP Tool)
Strategy Implementation Plan, Project Management and Risk Assessment | TBD | TBD | TBD | 2 | 4 | 8
Procurement KPI Reporting (Sourcing Portal)
Supplier Management and Reporting | TBD | TBD | TBD | 2 | 4 | 8
Distribution List Management & External User Provisioning
Partner Access Management | TBD | TBD | TBD | 1 | 2 | 2
Application Technical KT
Force.com
Understanding Data Model of the 4 applications - GOS, SIP, Sourcing Portal and Distribution List Management applications | TBD | TBD | TBD | 2 | 4 | 8
Salesforce Configuration - Analysis (Profile, Custom Objects, Permission Sets etc.) | TBD | TBD | TBD | 3 | 4 | 12
Salesforce Customization - Analysis (Apex, VF Pages, Lightning Components) | TBD | TBD | TBD | 6 | 4 | 24
Community Portal |  |  |  | 2 | 4 | 8
Community Portal Components | TBD | TBD | TBD | 1 | 4 | 4
Portal Configuration | TBD | TBD | TBD | 1 | 4 | 4
Wave Analytics |  |  |  | 2 | 4 | 8
Data model | TBD | TBD | TBD | 1 | 4 | 4
Data flow between Analytics and force.com applications | TBD | TBD | TBD | 1 | 4 | 4
Ancillary tools |  |  |  | 4 | 4 | 16
X-Author | TBD | TBD | TBD | 1 | 6 | 6
Conga | TBD | TBD | TBD | 1 | 1 | 1
Adobe e-Sign | TBD | TBD | TBD | 1 | 2 | 2
GridBuddy | TBD | TBD | TBD | 1 | 3 | 3
Odaseva Backup solution | TBD | TBD | TBD | 1 | 4 | 4
Integration |  |  |  | 4 | 3 | 12
Interface Overview | TBD | TBD | TBD | 2 | 3 | 6
Integration routines | TBD | TBD | TBD | 2 | 3 | 6
Support and Enhancement Operations KT
Current ITIL Processes, Overview of Incident Mgmt. and Service Request | TBD | TBD | TBD | 10 | 1 | 10
Lifecycle of Incident at TGF (Opening, review, workflow, processes, approvals, closing), Incident Reporting, Setting Priority to incidents, Ageing in Incidents, SLAs | TBD | TBD | TBD | 10 | 1 | 10
QA KT
Automation Testing Overview and Test Scripts | TBD | TBD | TBD | 4 | 4 | 16
Regression Testing Suite overview | TBD | TBD | TBD | 4 | 4 | 16
PROVAR and Selenum Tool Understanding | TBD | TBD | TBD | 4 | 4 | 16
PMO Toolkit review | TBD | TBD | TBD | 1 | 2 | 2
Environment Management KT
Configuration Management Process Understanding | TBD | TBD | TBD | 3 | 4 | 12
Understanding of Release Management | TBD | TBD | TBD | 3 | 4 | 12
Tool Overview : SonarQube, GitHub, Jenkins etc. | TBD | TBD | TBD | 4 | 4 | 16